## personal_project_planning_templ
Project Component | My Response/Plan
1. PROJECT DEFINITION
Project Name | SkillSync: Student Skill-Job Match Analyzer
Project Description | SkillSync is a web platform that helps Indian students bridge the gap between their current skills and job market demands. Students create profiles by entering their educational background, technical skills, and career interests. The system analyzes their profile against a curated database of job listings to identify skill gaps and provides personalized job recommendations.
Why is this important to me? | This project is important to me because it provides hands-on experience to enhance my web development skills, including MERN stack. It also serves as a portfolio piece that clearly demonstrates my abilities to potential employers or collaborators. Furthermore, it adds tangible value to my resume by showcasing practical application of my learning and commitment to growth.
What will I gain from completing this? | By completing this project, I will gain practical, hands-on experience in developing and deploying full-stack applications using the MERN stack. Additionally, I will improve my ability to solve real-world problems through coding, design, and implementation, which will enhance both my technical skills and my readiness for professional challenges.
Project Category (Learning/Creative/Health/Skill/Other) | Skill
2. GOAL SETTING
Main Goal (SMART format) | My main goal is to build my first complete web application called “SkillSync” using the MERN stack. This app will allow students to input their skills, view a curated list of jobs, and see basic skill matches. Specific: I will create a full-stack MERN application where users can register, add their skills, and browse jobs with simple keyword-based matching. Measurable: The project will include 3–4 frontend pages in React.js, 5–6 backend API endpoints in Node.js/Express, and 2 MongoDB collections (users and jobs). Users should be able to register, add skills, browse at least 100 sample jobs, and view matches. I will also maintain a GitHub repository with regular commits and a documented README. Achievable: I will start with static job data, simple forms, and straightforward keyword matching. This keeps the project realistic for a first full-stack build while letting me focus on learning MERN fundamentals like React components, Express routing, MongoDB operations, and API integration. Relevant: This project is portfolio-worthy because it solves a real-world problem I understand as a student: the skill-job mismatch. It also demonstrates my ability to build an end-to-end full-stack project, which is valuable for internships and job interviews. Time-bound: I will complete this project by November 28, 2025 (8 weeks). Weeks 1: Learn MERN basics, set up the environment, and build a simple frontend. Weeks 2: Build backend APIs, connect to MongoDB, and implement matching logic. Weeks 3: Integrate frontend with backend, add user authentication, and refine UI. Weeks 4: Deploy frontend (Vercel) and backend (Render/Railway), polish features, and document everything.
Success Criteria - How will I know I succeeded? | I’ll know I’ve truly succeeded when: I can confidently say: “I built a web application that actually solves a real problem using the MERN stack.” A hiring manager can look at my project and clearly understand what I’m capable of technically. I feel ready to take on more challenging projects or contribute to open-source MERN applications. Other students come to me asking how I built it, and I can guide them through the process. The biggest sign of success will be realizing that I’ve gone from learning the MERN stack to actually building with it.
Target Completion Date | 1930-11-01
Time Commitment per Week | 10 hours
3. PROJECT BREAKDOWN
Phase 1 - Tasks and Deadlines | Foundation & Frontend Setup
Phase 2 - Tasks and Deadlines | Backend Development & Database
Phase 3 - Tasks and Deadlines | Integration & Core Features
Phase 4 - Tasks and Deadlines | Enhancement, Deployment & Documentation
4. RESOURCES & REQUIREMENTS
Skills I need to learn/improve | MERN
Tools/Software/Equipment needed | vs code, git and postman
Budget/Cost considerations | 0
People who could help/advise me | None
5. MOTIVATION & ACCOUNTABILITY
What could derail this project?
How will I stay motivated?
Who will hold me accountable?
Rewards for milestones achieved
6. TRACKING & REVIEW
How often will I review progress? (Daily/Weekly/Monthly)
What metrics will I track?
Review dates scheduled in calendar
Adjustment plan if falling behind